## PREAMBLE
0. PREAMBLE
===============
This document was created in order to enable planning of reaching the beta quality for Free SCADA software (fs2).

1. GENERAL CONSIDERATIONS
===============
At the time, the works on fs2 are uncoordinated, everybody of us is keeping in mind his ideas, but has slightly different targets.
In my opinion, we should create a CENTRAL REGISTER of Versions, Features and Works, with namely associations between task and developer.
It is not necessary for it to be something complex, I think a simple file (perhaps this file) could be good enough.
Maybe we can utilize Feature Requests on SourceForge, but I have no experience with it, so I have created this file for first.

2. DYNAMIZATION
===============
To the crucial decision about the style of dynamization (actions vs bindings), after some analyze of the situation I think that we should:
- continue with bindings
- delete all the code and all the functionality of actions
Reasons:
- most of the functionality of actions can be achieved via bindings
- bindings are standard in wpf
- settings of action parameters is a little bit strange

3. CONTROLS ("SYMBOLS")
===============
My opinion in this direction is, that we need few types of in-built controls (symbols) for the most common purposes, instead of the use of wpf sliders, progress bars etc. / Usually we need more services from a schema control than the simple progress bar etc. can offer to us / (example - a valve: displaying of the status, possibility to send two commands, using two input variables for opened and closed state).
The control types are shown in the roadmap document (next page).

4. Archiver subsystem
===============
- In my opinion should be a normal part of Runtime exe and not a standalone service. This arrangement has sense if we have a full client/server architecture only.
- Cache object (receives value change events from plugins, creates some short history)
- Archiver working thread (sends values to SQL and a refresh event to charts(trends) and event lists)
- SQL DB: MS SQL server Express or Firebird Embedded? I would prefer embedded Firebird (no installation of MS SQL necessary) ...
- Parameterization: for each value: none, cycle or change driven archivation, time for cycle, archive art (current value, average value, maximal value etc.), trend buffer yes/no, trend buffer length

5. Possible future extension
===============
- scripting plugin: arbitrary computations above tag values, cyclic or event-driven

Very complex, but very valuable
===============
- softPLC programmed via Functional Block Diagramm (CAD - like language): / using the norm IEC61131-3 FBD: / - Graphic Editor - FBD language / - Variable editor (variable declaration) - data types Integer, Boolean, Float (no Structures and Arrays at the beginning) / - Library - Function Blocks of IEC (and, or etc, RS, JK etc, ramps, regulators, time blocks, edge blocks etc) / - Analyser of Graphical code (coverts blocks into function calls, lines into variables) / - Code generation to ANSI C-code, due to the possibility of porting softPLC "target" to other OSes / - Code compilation (gcc (mingw) configured with a generated makefile) into dll / - dll has inside: PLC code exported via a function, input data table and output data table / - SoftPLC frame exe (windows "target" - works in cyclic manner, imports dynamically the dll with PLC code compiled from graphic via gcc / - SoftPLC frame exe - can reload programm (via a command) using dynamic import of dll after reload / - Modbus/tcp interface for frame exe (modbus/tcp server) using data from dll input/output tables / - Modbus/tcp interface for freescada softPLC interface (modbus/tcp client) / - Ability to make "online test" - show the program execution in softPLC via CAD screen updates / - Examples of this functionality in commercial products: ISaGraf, Logicad32

## FS2 ROADMAP
TASK ID		Task source	Classes affected	Developer	Schedule	Target Revision
A	Step A (fixing of what we have now):	MICHAEL				BETA.1
A.1	All commands on the toolbar or menu should not be enabled if there is no applicability for this command. For example: / Adding new schema when we don’t have any project loaded or created. / Zooming function when there is nothing to Zoom (there is no any schema currently active)	MICHAEL				BETA.1
A.2	Fixing of multi-selection of graphic elements.	MICHAEL				BETA.1
A.3	Fixing of Copy to clipboard capabilities. We need to be able to copy&paste our elements. We need to be able to export copied to clipboard content to other application as a raster picture or vector graphic element. Need to decide which format is better.	MICHAEL				BETA.1
A.4	Ability to change Z order of selected element(s) (bring to top, bring to back)	MICHAEL				BETA.1
A.5	Ability to align selected element(s) (left, right, center, vertical or horizontal)	MICHAEL				BETA.1
A.6	Fix of Helper grid – ruler should work (users can turn it “on” or “off”), persistence in Schemas for user friendliness	MICHAEL				BETA.1
A.7	Deleting all code related to actions, Refactoring of dynamization using Data Binding and symbol libraries	PAVEL				BETA.1
A.8	Improvements of channel selection method. Currently there is simple text string. Therefore users will have no idea how to use it. Having something like a selection from project variables would help to avoid that.	MICHAEL				BETA.1
A.9	Availability of “rich” controls	MICHAEL				BETA.1
A.9.1	- commanded symbol control (changing predefined wpf content (drawing, image or text) (min 4 states), min. 2x input value (integer) representing 1-bit or 2-bit signal from technology, 2x command open/close (using e.g. context menu), showing status (validity, unacknowledged state etc))	PAVEL				BETA.1
A.9.2	- symbol control (changing predefined wpf content (drawing, image or text) (min 4 states), min. 2x input value (integer) representing 1-bit or 2-bit signal from technology, showing status (validity, unacknowledged state etc.))	PAVEL				BETA.1
A.9.3	- analog control (showing textual representation of a value (integer, double), showing status (validity, unacknowledged state etc.))	PAVEL				BETA.1
A.9.4	- bar control with scale	PAVEL				BETA.1
A.9.5	- button control for Triggers / - Triggers (user actions): / - setpoint value setting / - command initiation / - activating schemas	PAVEL				BETA.1
A.9.5		PAVEL				BETA.1
A.10	Progress bar has “style” property which brings a question to user for selecting some file. We need to avoid that in general. All available styles should be available via dropdown control. “custom” style is just one item from this list for advanced users.	MICHAEL				BETA.1
A.11	Content control has “content” property. When we show open file dialog, there should be appropriate filters on files. E.g. Graphic files (*.jpg, *.png). But it is not a typical to have reference to some external file. Every content entity should be embedded to the project file unless user says different / - bitmap import and saving in project file / - bitmap (image) object using saved bitmaps	MICHAEL				BETA.1
A.12	Property editor should have only relevant set of properties and each property should have a tooltip which describes it.	MICHAEL	ShortProp			BETA.1
A.13	- renaming items in project panel (F2 button)	PAVEL
A.14	- directory structure definition in project zip file and project panel	PAVEL
A.15	- context menu for project structure handling	PAVEL
A.16	- Library window for drag and drop of symbols into schema (Visio-alike)	PAVEL
A.17	- inplace online ("connected") modus for SchemaView (no need to run Runtime when testing a picture)	PAVEL
B	Step B. Improve communication layer.	MICHAEL				BETA.1
B.1	Extending BaseChannel with common functionality (Properties) for: Textual Description, Additional Texts, Unit, External Address info string, Acknowledge info and Alarm level etc.	PAVEL	BaseChannel	PAVEL	31.12.2008	BETA.1
B.2	OPC plug-in need ability not only read data from OPC, but should be able to write data to the server.	MICHAEL				BETA.1
B.3	MODBUS protocol support.	MICHAEL	MODBUSPlug.*	PAVEL	31.12.2008	BETA.1
B.4	It needs channel configuration dialog	MICHAEL	MODBUSPlug.*	PAVEL	31.12.2008	BETA.1
B.5	Ability to read and write values to the device.	MICHAEL	MODBUSPlug.*	PAVEL	31.12.2008	BETA.1
B.6	Connections through TCP and Serial ports.	MICHAEL	MODBUSPlug.*	PAVEL	31.12.2008	BETA.1
MILESTONE 1	Tag this version as BETA.1 and see users’ reports about our bugs! :)	PAVEL				BETA.1
C	Step C. Trend Control	MICHAEL				BETA.2
C.1	This is the simplest task. The only we need is a new graph control which can show trends of specified channels in real time mode. No any saving of this data needed.	MICHAEL				BETA.2
D	Step D. Event (Alarm) support.	MICHAEL				BETA.2
D.1	Create infrastructure for defining events for one or more channels.	MICHAEL				BETA.2
D.2	Designer needs new “document” window which will be used for event configuration.	MICHAEL				BETA.2
D.3	Schema elements should be able to refer to particular event. E.g. showing some indication of event state and be able to change this state.	MICHAEL				BETA.2
D.4	- two event sources: / - external (OPC A&E or OPC UA server via Event Notification objects) / - internal event generator object for values received via OPC DA or MODBUS etc. - events defined via OP / - Parameterization: / - creating general EventCondition and SubCondition objects / - Allocation of EventCondition objects to channels	PAVEL
MILESTONE 2	Tag this version as BETA.2 and see users’ reports about our bugs! :)	PAVEL				BETA.2
E	Step E. Historical data collection.	MICHAEL				BETA.3
E.1	Each project variable can be set for archiving.	MICHAEL				BETA.3
E.2	Flexible set of rules to define when and how to save the data. It should be edited by users. Probably we could use some of scripting language to create small snippets of code which will do all of this logic. Users can edit them manually or use some “wizard” to create of what they need.	MICHAEL				BETA.3
E.3	Ability to save changes of event states by following the same rules as project variables.	MICHAEL				BETA.3
E.4	The data is stored in SQL database via standard interfaces so users should be able to choose which database to use (MS SQL, Postgres, MySQL)	MICHAEL				BETA.3
F	Step F. Analysis of historical data and reporting.	MICHAEL				BETA.3
F.1	There are three fundamental ways to see historical data.	MICHAEL				BETA.3
F.2	Graphic trends for one or more variables.	MICHAEL				BETA.3
F.3	Table representation of one or more channels.	MICHAEL				BETA.3
F.4	“player” mode. Users can open their schema and use over the time navigation control to locate interesting points. The schema will show state of variables at requested point of time.	MICHAEL				BETA.3
F.5	Any of these views can be sent to the printer.	MICHAEL				BETA.3
F.6	Vector pictures: Graphic trends and current state of a schema in “player” mode.	MICHAEL				BETA.3
F.7	Simple text: Table view.	MICHAEL				BETA.3
F.8	Users can create they own queries for Trends and Table probably using SQL syntax. Those queries are saved in the project file for future usage.	MICHAEL				BETA.3
MILESTONE 3	Tag this version as BETA.3 and see users’ reports about our bugs! :)	PAVEL				BETA.3
G	Step G. Documentation	MICHAEL				BETA.4
G.1	We need as big as we can create help system for our applications.	MICHAEL				BETA.4
G.2	The help should be integrated into applications via help menu and context help.	MICHAEL				BETA.4
MILESTONE 4	Tag this version as RELEASE CANDIDATE.1 and see users’ reports about our bugs! :)	MICHAEL				RC.1
H	Step H. Remote access.	MICHAEL				RC.2
H.1	Ability to see schema in real time mode via browser	MICHAEL				RC.2
H.2	See predefined reports via browser.	MICHAEL				RC.2
H.3	We need to choose either to create separate “web application” or to use Real Time application as a server for that.	MICHAEL				RC.2
MILESTONE 5	Tag this version as RELEASE CANDIDATE.2 and see users’ reports about our bugs! :)	PAVEL				RC.2